## Budget
Item | Cost | How many | Total
Microbit | 12.99 | 1 | 12.99
Microbit Cable - Micro B 5-Pin Cable | 0.99 | 1 | 0.99
Battery Holder (optional) | 1.56 | 1 | 1.56
2 x AAA Battery (optional) | 6.99 | 1 | 6.99
22.53
Micro:Bit Kit |  |  | 14.99

## WBS
Microbit
Planning | Hardware |  | Software | Management
Decide on the project idea | Research how the parts work |  | Research how similar project have been done | Create a budget spreadsheet
See if the idea has been made | Begin to put parts together |  | Begin to code | Create a WBS
| Make sure the parts are correctly put together |  | Test the code | Create a gnatt chart
| Compile it with the software |  | Compile it with the hardware | Make sure the porject is within the budget and is completed on time while still maintaining high quality
| Record each step of building |  | Record each step of building
| Record any problems that were encountered |  | Record any problems that were encountered

## Gantt Chart
Date | 2017-09-26 | 2017-09-27 | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08
Research the hardware that will be needed
Create a budget
Create a gantt chart
Create a WBS
Collect the hardware
Begin the code
Begin the hardware
Test the hardware and code throughout building (unfinished) |  |  |  | *
Complete the code
Complete the hardware
Test the hardware and code thoughtout building (mostly finished) | [7 empty] | *
Find and fix any bugs/errors | [8 empty] | *
Create a step-by-step presentation
Create a PDF tutorial
Import all to github | [10 empty] | *